## Register
Sheet No | Title | Discipline | Stage | Owner | Planned date | Package
A-120 | Fifth Floor Plan (future) | A | Working drawings / GFC | Meghna Joshi | 15-12-2026 | Arch GFC set
A-121 | Roof Plan | A | Working drawings / GFC | arjun.pillai@firm.example | 18-Dec-2026
M-212 | Kitchen Exhaust Layout - Ground Floor | M | Working drawings / GFC | Rahul Kumar | 2026-12-04 | HVAC GFC set
M-213 | Laundry Exhaust Layout - Basement | M | Working drawings / GFC | Kavya Hegde | 07/12/2026
E-120 | Lightning Arrester Layout - Terrace | E | Working drawings / GFC | Rohan Das | 10-12-2026
A-101 | Ground Floor Plan | A | Working drawings / GFC | Meghna Joshi | 01-12-2026
Q-301 | Kitchen Equipment Layout | Q | Working drawings / GFC |  | 05-12-2026
P-120 | Rainwater Harvesting Details | P | Working drawings / GFC | Imran Khan | 31-11-2026